CIS 4374 Homework 5

1.The software that I picked to research that already exists in TaskMaster Pro. The proposed application fills critical gaps in the existing software landscape by combining automation, usability, scalability and modern design. This research establishes the foundation for the system’s unique value proposition.

The application will be different by itself by offering:

- Modern, intuitive interface

- Automated workflows

- Real-time collaboration

- Advanced analytics dashboards

- Role-based access control

- Seamless integration with third-party tools

- Scalable cloud architecture

2. The project was acquired after the fictional company NovaTech Solutions, a mid-sized software development firm, responded to a Request for Proposal issued by a client seeking modernization of their internal workflow system. NovaTech was selected due to its strong track record in custom enterprise applications and its reputation for delivering scalable user-friendly solutions.

3. 15 Use Cases for SRS Draft

- User Login

- User Logout

- Create Workflow

- Edit Workflow

- Delete Workflow

- Assign Task

- Complete Task

- Generate Report

- View Dashboard

- Manage User Roles

- Receive Notification

- Search Tasks

- Upload File

- Export Data

- System Backup

Parking App Work Breakdown Structure

- Authentication Module: This section covers all functionality related to secure user access. It includes login, registration, and session management. Tasks span UI design, credential validation, and token-based session handling. This module ensures that only authorized users can access the system and that sessions are properly maintained.

- User and Operator Management: This component focuses on creating, editing, and managing user and operator accounts. It includes workflows for adding users, assigning roles, and maintaining account profiles. Audit logging and account deactivation are also included to support administrative oversight and compliance.

- Dashboards: Dashboards form the core user interface for both customers and operators. This section includes garage management (add/edit/remove garages), parking search and selection, and payment processing. It represents the main interactive portion of the app where users find parking, reserve spots, and complete transactions.

- Reporting Module: Reporting provides visibility into system performance and financial activity. It includes occupancy graphs, transaction summaries, and exportable reports. This module supports decision-making by offering analytics, trends, and operational insights for administrators.

- System Infrastructure: This section defines the technical foundation of the application. It includes database design, API development, and cloud deployment. Tasks cover schema creation, backend service development, and performance optimization. This ensures the system is scalable, reliable, and capable of supporting real-time operations.

- Quality Assurance: Quality Assurance ensures the system meets functional, performance, and security requirements. It includes functional testing for each module, stress and load testing, and security validation such as vulnerability scanning and role-based access verification. This section guarantees that the final product is stable and secure.

- Project Management: This final section covers documentation, meetings, and delivery activities. It includes SRS creation, WBS and Gantt chart development, client reviews, sprint planning, and final deployment. It ensures the project stays organized, documented, and aligned with stakeholder expectations.

Parking App Timeline

Week 1 — Requirements & Planning

- Finalize SRS draft

- Complete WBS (3 levels)

- Identify actors & use cases

- Initial project schedule

Week 2 — System Architecture & Design

- Database schema design

- API structure planning

- UI wireframes for dashboards

- Authentication workflow design

Week 3 — Core Development (Phase 1)

- Authentication module

- User & operator management

- Session handling

- Basic navigation

Week 4 — Core Development (Phase 2)

- Garage management dashboard

- Parking finder

- Payment integration

- File upload & export features

Week 5 — Reporting & Infrastructure

- Occupancy graphs

- Financial reports

- Cloud deployment setup

- API integration testing

Week 6 — QA, Finalization & Delivery

- Functional testing

- Performance testing

- Security testing

- Final documentation

- Deployment & handoff

Smart Parking App

  - Risk By Category

| Category | Potential Risks |
| --- | --- |
| Technical | • Integration failure between mobile app and cloud database • API latency or downtime affecting real-time parking updates • Data security vulnerabilities (user credentials, payment info) • Inaccurate sensor data or IoT device malfunction |
| Schedule | • Delays in requirements gathering or stakeholder approval • Dependencies on third-party APIs slowing development • Testing phase overruns due to bug volume • Late delivery of UI/UX assets or wireframes |
| Financial | • Budget overrun from unexpected hardware costs • Licensing fees for mapping or payment services • Insufficient funding for maintenance post-launch • Cost of cloud hosting exceeding estimates |
| People | • Team skill gaps in mobile or backend development • Communication breakdown between developers and project manager • Stakeholder disengagement or unclear expectations • High turnover or absenteeism during critical sprints |

  - Risk Register

| ID | Risk Description | Category | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| R1 | API integration failure | Technical | Medium | High | Conduct early API testing and mock data validation |
| R2 | Sensor data inaccuracies | Technical | High | Medium | Implement calibration and redundancy checks |
| R3 | Schedule slip due to design delays | Schedule | Medium | High | Enforce design deadlines and weekly progress reviews |
| R4 | Budget overrun from cloud costs | Financial | Medium | High | Monitor usage and optimize resource allocation |
| R5 | Payment gateway security breach | Technical | Low | High | Use PCI-compliant encryption and regular audits |
| R6 | Team communication breakdown | People | Medium | Medium | Weekly sync meetings and shared documentation |
| R7 | Stakeholder feedback delays | Schedule | High | Medium | Set fixed review windows and escalation paths |
| R8 | Developer turnover mid-project | People | Low | High | Maintain documentation and cross-training |
| R9 | Insufficient post-launch support funds | Financial | Medium | Medium | Allocate contingency budget for maintenance |
| R10 | Testing phase overruns | Schedule | High | High | Parallelize testing and automate regression checks |

  - Communication Plan

| Team / Stakeholder | Meeting Cadence | Reporting Method |
| --- | --- | --- |
| Project Team (Dev, QA, PM) | Twice weekly (Mon & Thu) | Microsoft Teams + shared OneNote |
| Client / Stakeholders | Bi-Weekly | Email summary + dashboard report |
| Executive Sponsor | Monthly | Executive summary report |
| Cross-functional (Design, Infra) | Weekly | Stand-up meeting |
| Ad-hoc Risk Review | As needed | Risk Register updates |

  - Roles and Resources

| Role | Name (Fictional) | Skill Level | % Allocation | Key Responsibilities |
| --- | --- | --- | --- | --- |
| Project Manager | Ava Thompson | Senior | 25% | Oversees schedule, deliverables, and client communication. |
| Lead Developer | Carlos Nguyen | Expert | 30% | Designs architecture, leads backend & API development. |
| UI/UX Designer | Lena Patel | Intermediate | 20% | Creates wireframes, dashboard layouts, and user flows. |
| QA Engineer | Marcus Lee | Intermediate | 15% | Conducts testing, verifies security and performance. |
| Cloud Engineer | Sofia Ramirez | Senior | 10% | Manages deployment, scalability, and infrastructure setup. |

Assumption: Team members work part-time across a 6-week sprint cycle, totaling 100% combined allocation.

  - Resource and Cost Plan (Bottom – Up)

| Category | Resource | Hours | Rate ($/hr) | Cost ($) |
| --- | --- | --- | --- | --- |
| Project Management | Ava Thompson | 60 | 70 | 4,200 |
| Development | Carlos Nguyen | 80 | 65 | 5,200 |
| Design | Lena Patel | 50 | 55 | 2,750 |
| QA & Testing | Marcus Lee | 40 | 50 | 2,000 |
| Cloud Infrastructure | Sofia Ramirez | 30 | 60 | 1,800 |
| Total Estimated Cost |  |  |  | 15,950 |

Top – Down Monthly Cash Flow

| Month | Planned Spend ($) | Notes |
| --- | --- | --- |
| October | 8,000 | Design + Core Development (Phase 1) |
| November | 7,950 | QA, Reporting, and Final Deployment |

Budget Notes: Includes labor, minor cloud hosting fees, and testing tools. No hardware or licensing costs assumed.

  - RACI Matrix

| Task | Responsible ® | Accountable (A) | Consulted © | Informed (I) |
| --- | --- | --- | --- | --- |
| Authentication Module | Carlos | Ava | Lena | Marcus |
| User & Operator Management | Carlos | Ava | Marcus | Sofia |
| Dashboards | Lena | Ava | Carlos | Marcus |
| Reporting Module | Marcus | Ava | Carlos | Sofia |
| System Infrastructure | Sofia | Ava | Carlos | Marcus |
| Quality Assurance | Marcus | Ava | Carlos | Lena |
| Project Documentation | Ava | Ava | All | Client |